## Roadmap FONDI
ROADMAP FONDI — MAGGIO 2026
Robot Trader 2026 ¦ Fuerte Venture Capital ¦ Roadmap Development Week 1-4
Task | Fase | Start Date | End Date | Duration (Days) | Owner | Status | Week 1 (May 4-7) | Week 2 (May 11-14) | Week 3 (May 18-21) | Week 4 (May 25-28) | % Complete | Notes
Setup FONDI Module | Foundation | 04-May-2026 | 07-May-2026 | 4 | Claude | In Progress | X |  |  |  | 100% | DB schema + API
Implement Data Fetcher | Foundation | 04-May-2026 | 07-May-2026 | 4 | Claude | In Progress | X |  |  |  | 50% | Yahoo Finance integration
FONDI Screening Filters | Core | 08-May-2026 | 14-May-2026 | 7 | Claude | Planned |  | X |  |  | 0% | TER, Asset Class, Risk
Email Integration | Core | 08-May-2026 | 10-May-2026 | 3 | Claude | Planned |  | X |  |  | 0% | Email notifier update
Unit Tests FONDI | QA | 12-May-2026 | 14-May-2026 | 3 | Claude | Planned |  | X |  |  | 0% | Coverage + edge cases
API Endpoints | Integration | 15-May-2026 | 18-May-2026 | 4 | Claude | Planned |  |  | X |  | 0% | /fondi/screen, /fondi/results
FONDI Scheduler Setup | Operations | 19-May-2026 | 21-May-2026 | 3 | Claude | Planned |  |  | X |  | 0% | Daily 08:05 execution
Integration Tests | QA | 19-May-2026 | 21-May-2026 | 3 | Claude | Planned |  |  | X |  | 0% | Full flow testing
FONDI LIVE (May 21) | Launch | 21-May-2026 | 21-May-2026 | 1 | Luciano | Planned |  |  | X |  | 0% | 🚀 Go Live!
MILESTONE TRACKER
May 4 | Week 1 Start | FONDI Module Foundation | ✅
May 7 | Week 1 End | Core components ready | ✅
May 14 | Week 2 End | Filters + API complete | ⏳
May 21 | FONDI LIVE | 🚀 Public Release | ❌
VISUAL TIMELINE
Week 1 (May 4-7) Week 2 (May 11-14) Week 3 (May 18-21) Week 4 (May 25-28) ├─ Setup Module ├─ Implement Filters ├─ Scheduler Setup ├─ Buffer/Monitoring ├─ Data Integration ├─ Email Notifier ├─ FONDI LIVE (21) └─ Post-launch ├─ Basic Testing └─ Unit Tests └─ Integration Tests optimizations REVENUE TARGET: €113K by September 2026 (€57K from FONDI + €56K from other modules)